## FSO EXAMPLE
Driving Mechanic FSO
Game Designer : Alex Programmer : Daniela
Overview
How the player controls vehicles in the game
Production
Controls and Mechanics | Delivery | Dev Status | QC Status
Activity
The player can control a vehicle by going within [1] meter of the vehicle and pressing [X] | Proto | Done | OK
Player Controls
The player can accelerate using [RT] | Proto | Done | OK
The player can brake using [LT] | Proto | Done | OK
The player can turn the vehicle using the [Left joystick] | Proto | Done | OK
The player can turn the camera using the [Right joystick] | Proto | Done | NOT OK
The player can shoot using [X] | Proto | Done | NOT OK
Vehicle physics
Vehicles have inertia, depending on their [weight] | Proto | Done | OK
Vehicles have [5] hit points | Final unpolished | Done | OK
When a vehicle crashes at more than [50] mph, it is destroyed | Final unpolished | Done | NOT OK
The player respawns at the location where they entered the vehicle | Final unpolished | Done | OK
If the vehicle crashes at less than [50] mph, it takes [1] point of damage | Final unpolished | Done | OK
If the number of points of damage reaches the total vehicle hit points, the vehicle is destroyed | Final unpolished | TODO
The player respawns at the location where they entered the vehicle | Final unpolished | TODO
Art - UI
The TIMER appears in the UI on [TOP CENTER] of the screen | Final unpolished | TODO
The indication of speed appears in the UI on [BOTTOM RIGHT] of the screen | Final unpolished | TODO
The vehicle hit points appear in the UI on the [BOTTOM LEFT] of the screen | Final unpolished | Done | OK
Art - 3D
3D model for the vehicle | Proto | Done | OK
3D model for the driver | Proto | Done | OK
FX
Visual FX when the vehicle idles | Final unpolished | Done | OK
Visual FX when the vehicle accelerates | Final polished | TODO
Visual FX when the vehicle brakes | Final polished | TODO
Visual FX when the vehicle takes damage | Final polished | TODO
Visual FX when the vehicle is destroyed | Final polished | TODO
Animation
The driver has animations when the vehicle accelerates | Final polished | TODO
The driver has animations when the vehicle brakes | Final polished | TODO
The driver has animations when the vehicle takes damage | Final polished | TODO
Sound/Music Design
Audio FX when the vehicle idles | Final unpolished | Done | OK
Audio FX when the vehicle accelerates | Final unpolished | Done | NOT OK
Audio FX when the vehicle brakes | Final unpolished | TODO
Audio FX when the vehicle takes damage | Final unpolished | TODO
Audio FX when the vehicle is destroyed | Final unpolished | Done | OK
Additional Resources (reference images, charts, articles)
LEGEND
| Proto | Required that the feature be in the Prototype state
| Final unpolished | Required that the feature be complete for the game, but can be more polished
| Final polished | Polish for the feature to gain extra quality

## FSO TEMPLATE
FSO
Game Designer : Programmer :
Overview
Production
Controls and Mechanics | Delivery | Dev Status | QC Status
Art - UI
Art - 3D
FX
Animation
Sound/Music Design
Additional Resources (reference images, charts, articles)